## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US100 | As a user, I want to register and log in so that I can securely access my bank account. | MUST HAVE | None | Shreyash Shinde | 3 - Completed
Sprint 1 | Sprint 1 | US101 | As a user, I want to view my account balance so that I can check my available money anytime. | MUST HAVE | US100 | Shreyash Shinde | 3 - Completed
Sprint 1 | Sprint 1 | US102 | As a user, I want to deposit money so that I can increase my account balance. | MUST HAVE | US100 | Shreyash Shinde | 3 - Completed
Sprint 1 | Sprint 1 | US103 | As a user, I want to withdraw money so that I can access my funds when needed. | MUST HAVE | US102 | Shreyash Shinde | 3 - Completed
Sprint 1 | Sprint 1 | US104 | As a user, I want input validation for deposits and withdrawals so that I cannot enter invalid or negative values. | MUST HAVE | US102, US103 | Shreyash Shinde | 3 - Completed
Sprint 1 | Sprint 1 | US105 | As a user, I want to get confirmation messages after each transaction so that I know it was successful. | SHOULD HAVE | US103 | Shreyash Shinde | 3 - Completed
Sprint 2 | Sprint 2 | US106 | As a user, I want to transfer money between two accounts so that I can send money easily. | MUST HAVE | US102, US103 | Shreyash Shinde | 3 - Completed
Sprint 2 | Sprint 2 | US107 | As a user, I want to view my transaction history so that I can track all deposits, withdrawals, and transfers. | MUST HAVE | US106 | Shreyash Shinde | 3 - Completed
Sprint 2 | Sprint 2 | US108 | As a user, I want to download my transaction history as an Excel file using my account number for record-keeping. | SHOULD HAVE | US107 | Shreyash Shinde | 3 - Completed
Sprint 2 | Sprint 2 | US109 | As an admin, I want to view all user accounts and transaction histories so that I can monitor suspicious activities. | MUST HAVE | US107 | Shreyash Shinde | 3 - Completed
Sprint 2 | Sprint 2 | US110 | As an admin, I want to deactivate or activate a user account if suspicious transactions are detected. | MUST HAVE | US109 | Shreyash Shinde | 3 - Completed
Sprint 2 | Sprint 2 | US111 | As a user, I want to receive an error if my account is deactivated and be prompted to contact the admin. | MUST HAVE | US110 | Shreyash Shinde | 3 - Completed
Sprint 3 | Sprint 3 | US112 | As a user, I want to get an email notification after each successful transaction so that I have proof of the transfer. | MUST HAVE | US106 | Shreyash Shinde | 3 - Completed
Sprint 3 | Sprint 3 | US113 | As a receiver, I want to receive an email confirmation when I get money so that I can verify deposits. | MUST HAVE | US106 | Shreyash Shinde | 3 - Completed
Sprint 3 | Sprint 3 | US114 | As a user, I want invalid login or transaction attempts to display clear error messages so that I can correct them. | MUST HAVE | US100, US106 | Shreyash Shinde | 3 - Completed
Sprint 3 | Sprint 3 | US115 | As an admin, I want to generate reports summarizing all transactions to review system performance. | SHOULD HAVE | US109 | Shreyash Shinde | 3 - Completed
Sprint 3 | Sprint 3 | US116 | As a developer, I want transactions to be atomic so that partial failures don’t corrupt data. | MUST HAVE | US106 | Shreyash Shinde | 3 - Completed
Sprint 3 | Sprint 3 | US117 | As a user, I want to reset my password if forgotten so that I can regain access to my account. | SHOULD HAVE | US100 | Shreyash Shinde | 3 - Completed
Sprint 4 | Sprint 4 | US118 | As a user, I want to perform all banking operations from a user-friendly frontend integrated with the backend. | MUST HAVE | US100–US117 | Shreyash Shinde | 3 - Completed
Sprint 4 | Sprint 4 | US119 | As a user, I want frontend form validations and alerts so that I cannot submit invalid data. | MUST HAVE | US118 | Shreyash Shinde | 3 - Completed
Sprint 4 | Sprint 4 | US120 | As a developer, I want to integrate backend APIs with the frontend so that the entire system works end-to-end. | MUST HAVE | US118 | Shreyash Shinde | 3 - Completed
Sprint 4 | Sprint 4 | US121 | As an admin, I want to monitor transaction logs and deactivate suspicious accounts in real-time. | MUST HAVE | US110 | Shreyash Shinde | 3 - Completed
Sprint 4 | Sprint 4 | US122 | As a user, I want to log out securely so that my session ends safely and data remains protected. | MUST HAVE | All previous sprints | Shreyash Shinde | 3 - Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 85 | 44 | 38 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG ( Project Setup & Configuration (US ID: US1))
US100 | T100 | Initialize backend structure & Maven setup | 2025-08-20 | 2025-08-20 | Shreyash | Setup | 3 - Completed | 2 | Day 1: 2; Day 2: 0; Day 3: 0
| T101 | Configure MySQL DB and DBConfig class | 2025-08-20 | 2025-08-21 | Shreyash | Database | 3 - Completed | 4 | Day 1: 2; Day 2: 2; Day 3: 0
| T102 | Setup REST Application & CORS Filter | 2025-08-21 | 2025-08-22 | Shreyash | Coding | 3 - Completed | 4 | Day 1: 2; Day 2: 2; Day 3: 0
| T103 | Implement DatabaseInitializerListener for automatic table creation | 2025-08-22 | 2025-08-23 | Shreyash | Database | 3 - Completed | 5 | Day 1: 3; Day 2: 2; Day 3: 0
| T104 | Integrate Jakarta Mail for notifications | 2025-08-23 | 2025-08-24 | Shreyash | Integration | 3 - Completed | 3 | Day 1: 1; Day 2: 2; Day 3: 0
| T105 | Setup JUnit + Mockito for backend testing | 2025-08-25 | 2025-08-26 | Shreyash | Unit Test | 3 - Completed | 4 | Day 1: 2; Day 2: 2; Day 3: 0
SPRINT 2 (Backend API Development)
US101 | T106 | Create API for User Authentication (Signup/Login) | 2025-08-27 | 2025-08-28 | Shreyash | Coding | 3 - Completed | 6 | Day 1: 3; Day 2: 2; Day 3: 1
| T107 | Create API for Customer Management (add, update, delete, view) | 2025-08-28 | 2025-08-30 | Shreyash | Coding | 3 - Completed | 6 | Day 1: 3; Day 2: 2; Day 3: 1
| T108 | Create API for Account Management (create, update, delete, view) | 2025-08-30 | 2025-09-01 | Shreyash | Coding | 3 - Completed | 5 | Day 1: 3; Day 2: 2; Day 3: 0
| T109 | Create Transaction API (fund transfer, validation) | 2025-09-01 | 2025-09-02 | Shreyash | Coding | 3 - Completed | 5 | Day 1: 2; Day 2: 3; Day 3: 0
| T110 | Test all APIs using Postman + JUnit | 2025-09-02 | 2025-09-02 | Shreyash | Unit Test | 3 - Completed | 3 | Day 1: 2; Day 2: 1; Day 3: 0
SPRINT 3 (Frontend Development)
US110 | T111 | Setup React project (Vite + TypeScript + Tailwind + ShadCN UI) | 2025-09-03 | 2025-09-04 | Shreyash | Setup | 3 - Completed | 4 | Day 1: 2; Day 2: 2; Day 3: 0
| T112 | Design Login & Signup pages with validation | 2025-09-04 | 2025-09-05 | Shreyash | Design | 3 - Completed | 4 | Day 1: 2; Day 2: 2; Day 3: 0
| T113 | Develop Customer Dashboard (CRUD + Search) | 2025-09-05 | 2025-09-07 | Shreyash | Coding | 3 - Completed | 6 | Day 1: 3; Day 2: 2; Day 3: 1
| T114 | Develop Account & Transaction Management UI | 2025-09-07 | 2025-09-08 | Shreyash | Coding | 3 - Completed | 5 | Day 1: 3; Day 2: 2; Day 3: 0
| T115 | Integrate Backend APIs (Axios + .env) | 2025-09-08 | 2025-09-09 | Shreyash | Integration | 3 - Completed | 4 | Day 1: 2; Day 2: 2; Day 3: 0
SPRINT 4 (Testing, Enhancement)
US120 | T116 | End-to-end testing (UI + API + DB) | 2025-09-10 | 2025-09-12 | Shreyash | Unit Test | 3 - Completed | 5 | Day 1: 3; Day 2: 2
| T117 | Fix bugs, validation errors & optimize performance | 2025-09-12 | 2025-09-14 | Shreyash | Coding | 3 - Completed | 4 | Day 1: 2; Day 2: 2
| T118 | Add Toast notifications & responsive UI | 2025-09-14 | 2025-09-15 | Shreyash | Design | 3 - Completed | 3 | Day 1: 1; Day 2: 2
| T119 | Final deployment & documentation | 2025-09-15 | 2025-09-16 | Shreyash | Deployment | 3 - Completed | 3 | Day 1: 1; Day 2: 2
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint | Day | Impediments | Action Taken
1 | 1 | None | Completed software setup (Java, MySQL, React, Tailwind) and initialized project structure.
| 2 | Confusion about backend architecture | Discussed layered architecture, roles of Controller, Service, Model, and DB layers.
| 3 | Unsure about REST API endpoints | Planned endpoints for login, customer management, account management, and transactions.
| 4 | Doubts in frontend UI flow | Discussed pages: login, signup, dashboard, customer & account pages.
| 5 | Errors in Spring Boot setup | Resolved STS and backend errors, verified server startup and DB connection.
| 6 | Integration concerns | Discussed frontend-backend integration using REST API and JSON format.
| 7 | None | Filled retrospection document and reviewed Sprint 1 progress.
Sprint | Day | Impediments | Action Taken
2 | 1 | None | Discussed database schema and relations between Customer, Account, Transaction, and User.
| 2 | Confused about service methods | Defined methods for onboarding customer, creating account, updating balances, transaction creation.
| 3 | Class diagram doubts | Prepared final class diagram with relations and methods.
| 4 | Errors during code integration | Debugged backend services and controllers; ensured APIs work correctly.
| 5 | Method workflow unclear | Discussed flow of methods: customer → account → transaction → Excel export.
| 6 | None | Final integration tested between backend layers and initial frontend calls.
Sprint | Day | Impediments | Action Taken
3 – Frontend | 1 | None | Planned fields for landing page, login, and registration forms.
| 2 | None | Implemented user controller and integrated APIs for login/signup.
| 3 | None | Designed user profile pages and account overview pages.
| 4 | None | Updated registration page with validations and error messages.
| 5 | UI responsiveness issues | Applied Tailwind styling & ShadCN components; verified responsive layout.
| 6 | None | Tested integration of CRUD operations for Customers & Accounts with UI.
| 7 | Excel export UI not working | Integrated Apache POI and connected export button to API.
Sprint | Day | Impediments | Action Taken
4 – Final Integration | 1 | Security concerns | Implemented PIN validation, user active/inactive check, and input masking.
| 2 | Unauthorized access issues | Configured Protected Routes and role-based dashboard access.
| 3 | Transaction flow errors | Tested fund transfer scenarios, verified DB updates, and success responses.
| 4 | None | Completed final integration and end-to-end testing.
| 5 | Deployment queries | Deployed backend server & frontend locally, verified REST API connectivity.
| 6 | None | Filled final retrospection and project summary.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2025-08-25 | 2025-09-10 | Shreyash Shinde | Backend Setup | Nothing | API Development | Done everything.
2 | 1 | 2025-08-25 | 2025-09-10 | Shreyash Shinde | Database Design | Nothing | Coding | Done everything.
3 | 1 | 2025-08-25 | 2025-09-10 | Shreyash Shinde | Backend Validation | Nothing | Integration | Done everything.
4 | 2 | 2025-09-11 | 2025-09-25 | Shreyash Shinde | Frontend Integration | Nothing | Backend Testing | Done everything.
5 | 2 | 2025-09-11 | 2025-09-25 | Shreyash Shinde | Authentication | Nothing | API Connection | Done everything.
6 | 2 | 2025-09-11 | 2025-09-25 | Shreyash Shinde | Excel Export Feature | Nothing | Coding | Done everything.
7 | 3 | 2025-09-26 | 2025-10-10 | Shreyash Shinde | UI Enhancement | Nothing | Frontend Improvement | Done everything.
8 | 3 | 2025-09-26 | 2025-10-10 | Shreyash Shinde | Testing | Nothing | Debugging | Done everything.
9 | 4 | 2025-10-11 | 2025-10-25 | Shreyash Shinde | Nothing | Nothing | Final Testing and Optimization | Done everything.