## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Shreyash | 2025-09-01 | Login fails when email has uppercase letters | Sprint 2 | Shreyash Shinde | Functional | Converted email to lowercase before DB check | 2025-09-01 | Closed | Works fine now
2 | Shreyash | 2025-09-05 | Fund transfer succeeds with wrong PIN | Sprint 2 | Shreyash Shinde | Security | Added stricter PIN verification | 2025-09-05 | Closed | Tested successfully
3 | Shreyash | 2025-09-08 | Excel export misses recent transactions | Sprint 3 | Shreyash Shinde | Functional | Refresh cache before export | 2025-09-08 | Closed | Verified all transactions exported
4 | Shreyash | 2025-09-12 | Customer search slow for >1000 records | Sprint 3 | Shreyash Shinde | Performance | Added frontend filtering + pagination | 2025-09-12 | Closed | Load time improved
5 | Shreyash | 2025-09-15 | User dashboard shows wrong status for recently deactivated users | Sprint 3 | Shreyash Shinde | Functional | Update API to fetch live status | 2025-09-15 | Closed | Live status now correct
6 | Shreyash | 2025-09-18 | Create account allows duplicate account numbers | Sprint 3 | Shreyash Shinde | Functional | Added unique check before account creation | 2025-09-18 | Closed | Prevents duplicates
7 | Shreyash | 2025-09-20 | Password not masked in frontend forms | Sprint 2 | Shreyash Shinde | UI / Security | Added input type="password" | 2025-09-20 | Closed | Password hidden during typing
8 | Shreyash | 2025-09-22 | Invalid email formats accepted during signup | Sprint 2 | Shreyash Shinde | Validation | Added regex validation for emails | 2025-09-22 | Closed | Only valid emails allowed
9 | Shreyash | 2025-09-25 | Transaction amount > balance allowed | Sprint 3 | Shreyash Shinde | Security / Functional | Added balance check before transfer | 2025-09-25 | Closed | Transfer blocked if insufficient funds

## Sheet2
Logical
User Interface
Maintainability
Standards
Others